## BLANK - Sprint Planning
SPRINT PLANNING TEMPLATE
PROJECT NAME |  |  | PROJECT MANAGER |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE
NutriMate |  |  | John Paul Bolleser |  | 2025-06-12 | 2025-07-01 | 0% | SCOPE STATEMENT
At Risk? | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
| SPRINT 1 |  |  |  | 2025-06-10 | 2025-06-18 | 9 | In Progress | High
No | Create GitHub Repository for Collaboration | Version Control / Setup | Team |  | 2025-06-10 | 2025-06-10 | 1 | Complete | High | GitHub, README, Project Board, Branching Strategy
No | Project Environment Setup | Infrastructure / Setup | Team |  | 2025-06-12 | 2025-06-12 | 1 | Complete | High | Android Studio, Firebase SDK (Java), Firestore, Gradle, Figma
No | Account & Profile Setup | User Registration/Profile | Mendevil |  | 2025-06-12 | 2025-06-13 | 2 | Complete | Medium | Firebase Auth (Java), Java UI Components, BMI Calculation Logic
Yes | AI-Based Food Detection (YOLOv5) | AI / Computer Vision | Bolleser, Castañeda |  | 2025-06-14 | 2025-06-20 | 7 | Complete | High | YOLOv5 (PyTorch), OpenCV, TorchScript (Android), Python, UECFOOD-100 Dataset
| SPRINT 2 |  |  |  | 2025-06-19 | 2025-06-24 | 6 |  | High
No | Portion Input & Nutrition Calculation | Input & Logic | Bolleser |  | 2025-06-19 | 2025-06-21 | 3 | Complete | High | Java UI (EditText, Spinner), Java logic for nutrient calculation based on portion input
No | Food Database Integration | API / Backend | Tabiquero, Mendevil |  | 2025-06-19 | 2025-06-22 | 4 | Complete | Medium | USDA FoodData API / Open Food Facts, Retrofit (Java), Room DB
Yes | Meal Logging & Daily Planner | Backend / Data Tracker | Tabiquero, Mendevil |  | 2025-06-20 | 2025-06-24 | 5 | Complete | Medium | Firestore / Room (Java), MVVM (Java), LiveData, RecyclerView
| SPRINT 3 |  |  |  | 2025-06-25 | 2025-06-27 | 3 |  | Medium
No | Smart Assistant (Suggestions/Feedback) | NLP / Feedback UI | Bolleser, Castañeda |  |  |  |  | On Hold | Medium | Dialogflow API, Google ML Kit (Java), NotificationManager (Java), Conditional Logic (Java)
No | Progress Visualization (Charts & Stats) | UX / Visualization | Team |  |  |  |  | On Hold | Low | MPAndroidChart (Java), Java UI, ViewModel (Java), Bar/Line Graphs
No | Testing & Bug Fixing | QA / Testing | Team |  | 2025-06-27 | 2025-07-01 | 5 | Complete | High | JUnit (Java), Espresso (Java), Firebase Crashlytics, Manual QA Sheet, GitHub Issue Tracker
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.